## Sheet1
Application Name | GET_MOBANK_NEXT_OFFERS | Release Type | Others | Ticket Type | OneQ | Ticket Number |  | Vendor Name/Details
Reason for Release | New Release |  |  | Request Date | 2021-01-10 | Requester Name/Team | Prashant Yeshi
Implementation Plan | Release notes UAT Implementation Steps: App Deployment Team, Servers: 10.80.93.141/142 1. Please get the source code from "deliverables" in below mentioned svn. http://munmvs0905.ratnakarbank.in/svn/Enterprise_Services_Development/branches/NodeJsProjects/MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS Place the source code in /app 2. Do following environment and config changes set uat as running environment -Goto directory '/app/MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS/config' and open file 'config.js' -Find the line "process.env.NODE_ENV = 'dev' Replace 'dev' with 'uat' 3. Execute the following command npm config set store-dir /app/NodeLibs/ cd /app/ cd MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS/ pnpm i -r --offline 4. Execute below commands cd MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS/ pm2 start ecosystem.config.js 5. Nginx Configuration Please get the config files in below mentioned svn path. http://munmvs0905.ratnakarbank.in/svn/Enterprise_Services_Development/branches/NodeJsProjects/MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS/prop Login as root user and follow the mentioned step -- copy prop/conf.d/GET_MOBANK_NEXT_OFFER-upstrams.conf to /etc/nginx/conf.d/ -- copy prop/default.d/GET_MOBANK_NEXT_OFFER_locations.conf to /etc/nginx/default.d/ 6. check if nginx configuration is ok sudo nginx -t 8. Please start the nginx server if not started else use the below command to reload the settings sudo nginx -s reload |  |  |  | Roll Back Plan | Follow Below steps to stop server and restart the configruation Step 1: cd /app/MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS Step 2: pm2 stop ecosystem.config.js Step 3: netstat -nlp ¦ grep 4062 - If this command give below message then target server is stop. - Not all processes could be identified, non-owned process info Will not be shown, you would have to be root to see it all.) - else kill the corresponding process id Step 4: sudo systemctl reload nginx Step 5: sudo systemctl status nginx
Environment |  |  | Database Details |  |  | Release ID |  | Release Status
QA
QA Sign-Off |  | Yes
UAT | Servers: 10.80.93.141/142 User : appuser Port: 22 files: MOBANK_NEXT_OFFERS/GET_MOBANK_NEXT_OFFERS.zip, Nginx.conf
UAT Sign. Off |  | UAT Sign-Off By |  |  | UAT Release ID
Change Request No
Production
Change Status | [5 empty] | Final Comment from Release Manager
Note on G16: Sujay Sarkar: To be filled by Release Team
Note on I16: Sujay Sarkar: To be filled by Release Team
Note on G21: Sujay Sarkar: To be filled by Release Team
Note on I21: Sujay Sarkar: To be filled by Release Team
Note on G27: Sujay Sarkar: To be filled by Release Team
Note on I27: Sujay Sarkar: To be filled by Release Team
Note on H31: Sujay Sarkar: To be filled by Release Team