## Sheet1
Application Name | SUBMIT_CC_APPLICATION | Release Type | Others | Ticket Type | 1Q | Ticket Number | 51867 | Vendor Name/Details
Reason for Release | New deployment |  |  | Request Date | 22/4/2022 | Requester Name/Team | Prashant Yeshi
Implementation Plan | Release notes UAT Implementation Steps: App Deployment Team, Servers: 10.43.31.154 1. Please get the source code from ""deliverables"" folder in below mentioned svn. http://munmvs0905.ratnakarbank.in/svn/Enterprise_Services_Development/branches/NodeJsProjects/PREAPPROVED_AND_SECURE_CREDIT_CARDS/SUBMIT_CC_APPLICATION Place the source code in /app - cd /app - mkdir /app/PREAPPROVED_AND_SECURE_CREDIT_CARDS/SUBMIT_CC_APPLICATION - cd /app/PREAPPROVED_AND_SECURE_CREDIT_CARDS/SUBMIT_CC_APPLICATION - unzip -o SUBMIT_CC_APPLICATION.zip - docker build -t submit_cc_application:0.1 . - docker tag submit_cc_application:0.1 087203045977.dkr.ecr.us-east-1.amazonaws.com/preapproved_and_secure_credit_cards/submit_cc_application:0.1 - eval $(aws ecr get-login --no-include-email --region ap-south-1¦ sed 's¦https://¦¦') - docker push 087203045977.dkr.ecr.us-east-1.amazonaws.com/preapproved_and_secure_credit_cards/submit_cc_application:0.1 Kubernetes Server: 10.43.23.77 1. Place all K8 files from SVN Path to /kube/Projects/MOBANK - cd /kube/Projects/mobank/Configmaps - kubectl apply --force -f kube-submit-cc-application-api-configmap.yaml - cd /kube/Projects/mobank/ServiceEntry - kubectl apply --force -f kube-submit-cc-application-finacle-se.yaml - cd /kube/Projects/mobank/Services - kubectl apply --force -f kube-submit-cc-application-api-svc.yaml - cd /kube/Projects/mobank/VirtualSvc_DestRule - kubectl apply --force -f kube-submit-cc-application-vsdr.yaml - cd /kube/Projects/mobank/Deployments - kubectl apply --force -f kube-submit-cc-application-api-deployment.yaml |  |  |  | Roll Back Plan | Not Required as Initial Deployment
Environment | Application Details |  | Database Details |  |  | Release ID |  | Release Status
QA
QA Sign-Off |  | Yes
UAT | Server: 10.43.31.154 qa-user Server: 10.43.23.77 microservices port: 22
UAT Sign. Off |  | UAT Sign-Off By |  |  | UAT Release ID
Change Request No
Production
Change Status | [5 empty] | Final Comment from Release Manager
BugFix
Enhancement
Datapatch
Others
Note on G16: Sujay Sarkar: To be filled by Release Team
Note on I16: Sujay Sarkar: To be filled by Release Team
Note on G21: Sujay Sarkar: To be filled by Release Team
Note on I21: Sujay Sarkar: To be filled by Release Team
Note on G27: Sujay Sarkar: To be filled by Release Team
Note on I27: Sujay Sarkar: To be filled by Release Team
Note on H31: Sujay Sarkar: To be filled by Release Team